GOING MERRY PRIVATE LIMITED

HOSPITAL MANAGEMENT SYSTEM | BUSINESS REQUIREMENTS DOCUMENT

Client Review Baseline

| Document Version | 4.0 |
| --- | --- |
| Document Status | Draft — Client Review |
| Baseline Date | 29 August 2026 |
| BRD-Level Features | 78 business capabilities |
| Detailed SOW Decomposition | Approximately 100–150 detailed scope / delivery items |
| Scope Posture | Complete functional system within the approved problem statement; not an MVP |
| Primary Business Focus | Appointments + Smart Queue + Pharmacy Queue + Inventory |

Prepared for client requirement review and formal sign-off

# Document Control

| Item | Value | Owner | Status |
| --- | --- | --- | --- |
| Document | Business Requirements Document | Business Analyst | Draft |
| Version | 4.0 | Business Analyst | Current |
| Review Authority | Client | Client | Pending review |
| Architecture Authority | Solution Architecture | Solution Architect | Supporting artifact |
| Traceability | BRD → SOW → SRS → Backlog → Test | BA / SA / PM | Required |
| Change Model | Living baseline until sign-off; CR after sign-off | BA / Client | Defined |

## Revision History

| Version | Date | Change | Reason |
| --- | --- | --- | --- |
| 2.0 | Earlier baseline | 96 business-level features | Initial full-scope baseline |
| 3.0 / 3.1 | 29 Aug 2026 | 78 business-level features; scope boundaries and simplification rules | Consolidation and client-readiness |
| 4.0 | 29 Aug 2026 | Rebuilt structure, governance, assumptions, architecture alignment and review controls | Formal client review baseline |

# Table of Contents

This document uses Word heading styles. In Microsoft Word, right-click the field below and choose “Update Field” to refresh page numbers.

1. Purpose, Scope and Product Positioning

1.1 Scope Classification

1.2 Clarification vs Scope Expansion

1.3 Configuration Boundaries

2. Business Problem

3. Business Objectives

4. Stakeholders, Users and Responsibilities

4.1 Project Governance Team

User and Responsibilities

5. Product Channels

6. High-Level Functional Baseline — 78 Features

IAM — Identity, Access & Account Management — 5 Business Features

PAT — Patient Management — 4 Business Features

APT — Appointments & Referrals — 6 Business Features

SCH — Doctor Scheduling & Capacity — 4 Business Features

QUE — Check-in, Token & Queue Management — 6 Business Features

EMR — Clinical Encounter / EMR — 6 Business Features

DIA — Diagnostics — Laboratory & Radiology — 5 Business Features

PHA — Pharmacy & Medication Dispensing — 5 Business Features

INV — Inventory & Procurement — 6 Business Features

BIL — Billing & Payments — 6 Business Features

IPD — Inpatient / Ward Management — 5 Business Features

NOT — Notifications & Communications — 3 Business Features

REP — Dashboards, Reporting & Analytics — 5 Business Features

ADM — Administration & Configuration — 4 Business Features

AI — AI Decision Support — 4 Business Features

SEC — Security, Privacy & Compliance — 4 Business Features

6.1 Feature Count Summary

7. Cross-Functional Business Rules

8. Non-Functional Business Requirements

9. AI Decision-Support Requirements

10. End-to-End Business Journey

11. Solution Architecture Alignment

12. Assumptions and Dependencies

13. Scope Boundaries and Simplification Rules

13.1 Explicit Exclusions

14. SOW / SRS Decomposition and Traceability

15. Requirements Change Control

16. Acceptance and Sign-Off Criteria

17. Traceability Key

18. Client Review Checklist

# 1. Purpose, Scope and Product Positioning

This BRD defines the client-reviewable business baseline for a complete hospital management system within the approved academic/project problem statement. It is not an MVP. The 78 feature IDs represent business capabilities; the SOW/SRS will break those capabilities into detailed screens, rules, validations, workflows, acceptance criteria and delivery items.

Scope posture Complete functional hospital management project within the approved problem statement, with Appointment, Smart Queue, Pharmacy Queue and Inventory as the primary business scope.

The client may add, remove, clarify or change requirements during review.

No requirement becomes finally approved until formal BRD sign-off.

Feature IDs are stable traceability keys and must not be silently reused for materially different requirements.

A detailed SOW item is not automatically a new BRD feature.

The system supports the complete operational journey defined in this BRD without attempting every possible hospital enterprise capability.

## 1.1 Scope Classification

| Classification | Capabilities |
| --- | --- |
| Primary Scope | Appointment Management; Smart Queue Management; Pharmacy Queue; Inventory Management |
| Core Supporting Scope | Patient Management; Doctor Scheduling; EMR; AI Decision Support; Notifications; Dashboards; Security |
| Controlled Supporting Scope | Diagnostics; Billing; Inpatient / Ward Management |
| Platform Scope | Identity & Access; Administration; Azure deployment; monitoring; storage; messaging; operational controls |

## 1.2 Clarification vs Scope Expansion

A clarification explains or makes an existing approved capability testable without materially changing its business outcome. A scope expansion changes the outcome, users, integrations, data ownership, operational responsibility or external dependencies and therefore requires a Change Request.

| Clarification — normally allowed | Scope Expansion — controlled |
| --- | --- |
| Define appointment cancellation states | Add integrations with multiple external hospital systems |
| Define queue priority ordering for approved priority types | Add autonomous clinical diagnosis or treatment |
| Clarify fields needed for an existing patient record | Add a new hospital-wide operational domain not represented in the BRD |

## 1.3 Configuration Boundaries

Appointment slot duration

Queue priority rules

Low-stock thresholds

Reminder timing

Hospital / department master data

Other configurable business behavior requires documented approval through change control.

# 2. Business Problem

Hospital operations can become fragmented across registration, appointments, scheduling, queues, consultation, pharmacy, inventory, billing and reporting.

Patients need a predictable journey from registration through appointment/check-in, queue, consultation, prescription, pharmacy and completion.

Walk-ins, priority cases and doctor delays can create queue uncertainty and manual coordination.

Pharmacy teams need prescription-to-dispensing flow with inventory visibility, low-stock and expiry controls.

Management needs reliable operational KPIs, reports and practical forecasts.

Sensitive patient, clinical and financial information requires controlled access, auditability and recovery.

# 3. Business Objectives

Digitize the end-to-end outpatient journey and selected practical inpatient workflows.

Reduce avoidable waiting, scheduling conflicts and manual queue coordination.

Provide live queue visibility and useful estimated waiting time.

Connect consultation, prescription, pharmacy dispensing and inventory transactions.

Provide role-specific dashboards for patients, doctors, pharmacy, administration and management.

Use practical AI only as decision support for waiting time, no-show, queue and inventory forecasting.

Provide secure, auditable and maintainable services that can evolve through controlled client changes.

# 4. Stakeholders, Users and Responsibilities

## 4.1 Project Governance Team

| Role | Person | Responsibilities |
| --- | --- | --- |
| Project Manager | Sarthak Kanade | Planning, scope, schedule, risks, stakeholder communication and approval coordination |
| Tech Lead | Saurabh Yadav | Technical leadership, implementation standards, code quality and development coordination |
| Solution Architect | Ankit Verma | Architecture, scalability, integration, security and technology governance |
| Business Analyst | Rizwan Salmani | Requirements, BRD/SRS, process analysis, scope clarification and change documentation |
| Scrum Master | Sahil Shah | Sprint planning, ceremonies, coordination, impediment removal and process improvement |
| Client | Sayantan Ghosh | Business validation, feedback, review and formal scope approval |

4.2 Project Delivery Organization

Organization: Going Merry Private Limited
Project Type: Academic Industry-Oriented Software Engineering Project
Delivery Methodology: Agile Scrum

Primary Business Scope:
- Appointment Management
- Smart Queue Management
- Pharmacy Queue Management
- Inventory Management

# User and Responsibilities

| Stakeholder / Role | Primary Responsibilities |
| --- | --- |
| Patient | Registration, appointments, check-in, queue status, records, prescriptions, notifications, billing visibility |
| Doctor | Schedule, assigned patients, consultation, diagnosis, orders, prescriptions, results |
| Nurse / Clinical Staff | Triage, vitals, queue assistance, clinical support |
| Reception / Front Desk | Patient registration, appointments, check-in, queue operations |
| Pharmacist | Prescription review, medication dispensing, pharmacy queue and stock exceptions |
| Inventory / Procurement | Stock, batches, suppliers, purchase requests, receiving, transfers and replenishment |
| Billing / Finance | Charges, invoices, payments, refunds/adjustments and financial reporting |
| Administrator | Users, roles, master data, rules, configuration and reports |
| Management | KPIs, trends, utilization and operational reports |
| System Administrator | Technical configuration, monitoring and integration operations |

# 5. Product Channels

Patient web/mobile interface

Staff web portal

Doctor / clinical workspace

Pharmacy and inventory workspace

Billing workspace

Administration and management dashboard

Notification channels

# 6. High-Level Functional Baseline — 78 Features

The BRD counts business capabilities, not individual buttons, fields or validation rules. The SOW/SRS will decompose these capabilities into approximately 100–150 detailed scope/delivery items. This keeps the client-facing feature count manageable without turning the system into an MVP.

## IAM — Identity, Access & Account Management — 5 Business Features

| Feature ID | Business Feature |
| --- | --- |
| IAM-01 | Patient and staff authentication |
| IAM-02 | Registration and identity verification |
| IAM-03 | Password recovery and optional step-up authentication |
| IAM-04 | Session, account status and suspicious-login management |
| IAM-05 | Roles, permissions, profile and consent management |

## PAT — Patient Management — 4 Business Features

| Feature ID | Business Feature |
| --- | --- |
| PAT-01 | Patient master record and MRN management |
| PAT-02 | Demographics, contacts, emergency contacts and patient alerts |
| PAT-03 | Patient documents and record access |
| PAT-04 | Patient search, duplicate handling and correction |

## APT — Appointments & Referrals — 6 Business Features

| Feature ID | Business Feature |
| --- | --- |
| APT-01 | Doctor, department and service discovery |
| APT-02 | Availability and appointment slot search |
| APT-03 | Appointment booking |
| APT-04 | Appointment rescheduling and cancellation |
| APT-05 | Waitlist and referral management |
| APT-06 | Appointment lifecycle, history and reminders |

## SCH — Doctor Scheduling & Capacity — 4 Business Features

| Feature ID | Business Feature |
| --- | --- |
| SCH-01 | Doctor schedule and clinic session management |
| SCH-02 | Leave, holiday and urgent availability management |
| SCH-03 | Slot duration, capacity and room assignment |
| SCH-04 | Schedule exceptions, conflict detection and publishing |

## QUE — Check-in, Token & Queue Management — 6 Business Features

| Feature ID | Business Feature |
| --- | --- |
| QUE-01 | Patient check-in and eligibility validation |
| QUE-02 | Token generation and queue entry |
| QUE-03 | Live queue display and patient position |
| QUE-04 | Priority, emergency/triage and queue ordering rules |
| QUE-05 | Patient call, recall and turn management |
| QUE-06 | Queue transfer, pause, cancellation, no-show and fallback handling |

## EMR — Clinical Encounter / EMR — 6 Business Features

| Feature ID | Business Feature |
| --- | --- |
| EMR-01 | Clinical encounter creation and patient context |
| EMR-02 | Triage, vitals, observations and symptoms |
| EMR-03 | Medical, medication and relevant history |
| EMR-04 | Clinical notes and problem list |
| EMR-05 | Diagnosis, orders and prescription creation |
| EMR-06 | Encounter signing, follow-up and clinical history |

## DIA — Diagnostics — Laboratory & Radiology — 5 Business Features

| Feature ID | Business Feature |
| --- | --- |
| DIA-01 | Diagnostic test and service catalog |
| DIA-02 | Diagnostic order and scheduling |
| DIA-03 | Specimen/work queue management |
| DIA-04 | Result entry, verification and clinician review |
| DIA-05 | Diagnostic reports, critical-result alerts and patient viewing |

## PHA — Pharmacy & Medication Dispensing — 5 Business Features

| Feature ID | Business Feature |
| --- | --- |
| PHA-01 | Prescription queue and pharmacist validation |
| PHA-02 | Medicine/drug catalog |
| PHA-03 | Medication interaction and allergy warnings |
| PHA-04 | Medication dispensing and partial dispensing |
| PHA-05 | Dispensing history, refills, substitution and patient instructions |

## INV — Inventory & Procurement — 6 Business Features

| Feature ID | Business Feature |
| --- | --- |
| INV-01 | Medicine/item inventory and location management |
| INV-02 | Batch, expiry and stock status management |
| INV-03 | Stock ledger, adjustments and reconciliation |
| INV-04 | Inter-location stock transfer |
| INV-05 | Low-stock thresholds and alerts |
| INV-06 | Reorder requests, suppliers, purchase orders and goods receipt |

## BIL — Billing & Payments — 6 Business Features

| Feature ID | Business Feature |
| --- | --- |
| BIL-01 | Service and charge catalog |
| BIL-02 | Charge capture and invoice generation |
| BIL-03 | Discount, tax, waiver and pricing rules |
| BIL-04 | Payment collection and payment-status management |
| BIL-05 | Refunds, reversals and payment exception handling |
| BIL-06 | Receipts, statements, reconciliation and financial audit |

## IPD — Inpatient / Ward Management — 5 Business Features

| Feature ID | Business Feature |
| --- | --- |
| IPD-01 | Admission request and approval |
| IPD-02 | Bed, ward and occupancy management |
| IPD-03 | Patient admission, transfer and movement |
| IPD-04 | Inpatient care, medication and discharge coordination |
| IPD-05 | Discharge summary, final billing and follow-up tracking |

## NOT — Notifications & Communications — 3 Business Features

| Feature ID | Business Feature |
| --- | --- |
| NOT-01 | Notification preferences, consent and templates |
| NOT-02 | Appointment, queue, doctor-delay, prescription and operational notifications |
| NOT-03 | Delivery status, retry and communication history |

## REP — Dashboards, Reporting & Analytics — 5 Business Features

| Feature ID | Business Feature |
| --- | --- |
| REP-01 | Patient dashboard |
| REP-02 | Doctor and clinical dashboard |
| REP-03 | Pharmacy and inventory dashboard |
| REP-04 | Admin and operational dashboard |
| REP-05 | Management KPI, trend and scheduled reporting |

## ADM — Administration & Configuration — 4 Business Features

| Feature ID | Business Feature |
| --- | --- |
| ADM-01 | Hospital, department, room and master-data configuration |
| ADM-02 | User lifecycle, staff onboarding and administrative approvals |
| ADM-03 | Business rules and configurable workflow management |
| ADM-04 | System configuration, integration settings and operational administration |

## AI — AI Decision Support — 4 Business Features

| Feature ID | Business Feature |
| --- | --- |
| AI-01 | Waiting-time prediction |
| AI-02 | No-show prediction and appointment optimization |
| AI-03 | Queue optimization recommendations |
| AI-04 | Inventory demand forecasting and replenishment insight |

## SEC — Security, Privacy & Compliance — 4 Business Features

| Feature ID | Business Feature |
| --- | --- |
| SEC-01 | RBAC, least privilege and record/department-level authorization |
| SEC-02 | PII masking/tokenization and sensitive-data protection |
| SEC-03 | Encryption, secure storage, audit logging and security monitoring |
| SEC-04 | Backup, restore, retention and controlled emergency access |

## 6.1 Feature Count Summary

| Module | Count | Scope Classification |
| --- | --- | --- |
| IAM — Identity, Access & Account Management | 5 | Platform |
| PAT — Patient Management | 4 | Core Supporting |
| APT — Appointments & Referrals | 6 | Primary |
| SCH — Doctor Scheduling & Capacity | 4 | Core Supporting |
| QUE — Check-in, Token & Queue Management | 6 | Primary |
| EMR — Clinical Encounter / EMR | 6 | Core Supporting |
| DIA — Diagnostics — Laboratory & Radiology | 5 | Controlled Supporting |
| PHA — Pharmacy & Medication Dispensing | 5 | Primary |
| INV — Inventory & Procurement | 6 | Primary |
| BIL — Billing & Payments | 6 | Controlled Supporting |
| IPD — Inpatient / Ward Management | 5 | Controlled Supporting |
| NOT — Notifications & Communications | 3 | Core Supporting |
| REP — Dashboards, Reporting & Analytics | 5 | Core Supporting |
| ADM — Administration & Configuration | 4 | Platform |
| AI — AI Decision Support | 4 | Core Supporting |
| SEC — Security, Privacy & Compliance | 4 | Core Supporting |
| TOTAL | 78 | Business-level baseline |

# 7. Cross-Functional Business Rules

| Rule | Requirement |
| --- | --- |
| Authorization | Every protected action must be authorized server-side using role and, where needed, department/record scope. |
| Patient privacy | Users see only patient information necessary for their role and current business purpose. |
| Auditability | Sensitive create/update/delete/approve/access actions leave an auditable history. |
| State integrity | Appointment, queue, encounter, prescription, inventory, billing and admission states follow valid transitions. |
| Concurrency | Booking, queue and stock operations protect against duplicate or conflicting concurrent updates. |
| Notifications | Notifications respect preferences, consent, delivery state, retry and deduplication rules. |
| AI safety | AI outputs are advisory; normal workflows remain usable if AI is unavailable or low-confidence. |
| Configuration | Hospital-specific rules such as slot duration, priority and thresholds are configurable where practical. |

# 8. Non-Functional Business Requirements

| Area | Business Requirement |
| --- | --- |
| Security | TLS/HTTPS in transit, encryption at rest, secure secrets, RBAC, least privilege and audit logging. |
| Performance | Interactive patient/staff workflows should remain responsive under agreed expected concurrent usage. |
| Availability & resilience | Critical workflows should tolerate non-critical dependency failures and provide defined fallback behavior. |
| Scalability | Architecture should support growth in patients, appointments, transactions, documents, notifications and reports. |
| Usability | Interfaces should be responsive, consistent, accessible and appropriate to the user's role. |
| Data integrity | Transactional records must remain consistent, traceable and protected from silent destructive edits. |
| Observability | Application health, errors, queues, integrations, security events and AI behavior should be observable. |
| Recovery | Backup/restore and recovery objectives must be defined and tested before production sign-off. |
| Maintainability | APIs, events, configuration boundaries and ownership should be documented and versioned; critical workflows should have automated tests. |

# 9. AI Decision-Support Requirements

Waiting-time prediction uses queue length, doctor availability, consultation duration/history, appointment type and walk-in volume.

No-show prediction uses appointment history, prior cancellations, appointment timing and patient behavior patterns.

Queue optimization considers current queue, doctor availability, patient priority, appointment type and consultation time.

Inventory forecasting uses historical consumption, stock state and operational demand signals to support replenishment.

AI recommendations must not silently override authorized human decisions.

AI should expose useful confidence/context and have a deterministic non-AI fallback.

AI safety boundary AI is advisory only. Autonomous diagnosis, autonomous prescribing and autonomous treatment decisions are outside scope.

# 10. End-to-End Business Journey

| Stage | Business Step | Stage | Business Step |
| --- | --- | --- | --- |
| 1 | Patient registration / login | 2 | Doctor / service discovery |
| 2 | Availability & slot validation | 3 | Appointment or walk-in registration |
| 3 | Appointment / token creation | 4 | Check-in |
| 4 | Queue management | 5 | AI-assisted waiting-time estimate |
| 5 | Live queue tracking | 6 | Doctor consultation |
| 6 | Diagnostics / orders where required | 7 | Prescription |
| 7 | Pharmacy queue | 8 | Medicine dispensing |
| 8 | Inventory update | 9 | AI inventory forecast / reorder insight |
| 9 | Billing / payment | 10 | Completion and records |
| 10 | Notifications and reporting |  |  |

# 11. Solution Architecture Alignment

The BRD remains technology-neutral at the business requirement level, but the solution must align with the companion Software Architecture document. The architecture should implement the approved business capabilities without introducing unnecessary distributed-system complexity.

| Architecture Area | BRD Alignment |
| --- | --- |
| Client / Experience | Patient web/mobile experience plus role-specific staff interfaces. |
| API / Application Layer | A clear API boundary with modular business services. Appointment, queue, pharmacy, inventory, patient, clinical, billing and supporting capabilities have explicit ownership. |
| Business / Domain Layer | Business rules remain centralized and testable; state transitions and authorization are enforced server-side. |
| Data Layer | Transactional hospital records use a consistent relational data model; documents/files use secure object storage where required. |
| Async / Notifications | Events such as queue changes, appointment reminders, prescription readiness and low-stock alerts may use asynchronous messaging where it improves reliability. |
| AI Layer | AI models are isolated behind a service boundary and are decision-support only, with fallback to normal business rules. |
| Security Layer | Authentication, authorization/RBAC, encryption, PII protection, audit logging, secrets and recovery span the application. |
| Cloud / Operations | Azure deployment, monitoring, application health, logging, backups and operational configuration are managed consistently. |

Architecture principle Use a modular architecture first. Introduce separate deployable services only where there is a clear business, scaling, security or operational reason.

# 12. Assumptions and Dependencies

| Area | Assumption / Dependency |
| --- | --- |
| Business | The client is the authority for business scope and may change requirements during review. |
| Scope | The 78 BRD features are business capabilities; detailed implementation items are maintained in SOW/SRS. |
| Data | The project will use project-controlled sample/test data unless real production data is explicitly authorized. |
| External systems | Specific third-party integrations are not assumed until selected and approved. |
| Payments | A payment provider/adapter may be selected later if payment integration is required within the approved billing scope. |
| Diagnostics | Diagnostic workflows operate at catalog/order/work-queue/result/report level; specialist hardware integration is excluded. |
| Inpatient | Inpatient scope is practical admission, bed/ward movement, care/medication coordination and discharge, not every hospital department. |
| AI | Sufficient historical/operational data may be required for meaningful model evaluation; rule-based fallback remains mandatory. |
| Infrastructure | Azure services and deployment decisions must follow the companion SA document and project constraints. |
| Security | Access to sensitive data is limited to authorized roles and test environments must not expose unnecessary real PII. |

# 13. Scope Boundaries and Simplification Rules

No external medical-device integration unless explicitly approved.

External insurance / TPA claim processing is not assumed; basic insurance/billing information may be recorded where needed.

Payment gateway integration may use a selected provider/adapter; provider selection is a later decision.

Diagnostics are complete at order, work-queue, result-verification and report level; specialized laboratory hardware integration is excluded.

Inpatient functionality covers practical admission, bed/ward movement, care/medication coordination and discharge; it does not attempt every hospital department.

AI is decision support only and must have a normal-rule fallback.

No feature should be added solely to increase the feature count.

## 13.1 Explicit Exclusions

| Area | Explicitly Out of Scope Unless Approved by CR |
| --- | --- |
| Diagnostics | Laboratory machine integration; LIS/RIS; PACS; pathology automation; specimen logistics systems |
| Billing | Insurance claims; TPA integration; pre-authorization; adjudication; settlement workflows; accounting/ledger systems; external financial integrations |
| Inpatient | ICU, OT, NICU management; nurse rostering; ambulance management; housekeeping workflows; medical equipment management; meal planning; complex discharge planning |
| Administration | HRMS; payroll; recruitment; employee appraisal; attendance systems |
| Procurement | External supplier ERP integrations and automated procurement integrations |
| AI | Autonomous diagnosis; autonomous prescribing; autonomous treatment decisions |

# 14. SOW / SRS Decomposition and Traceability

The SOW will decompose the 78 BRD business capabilities into approximately 100–150 detailed scope/delivery items. These may describe screens, workflows, validations, business rules, notifications, integrations, audit behavior, edge cases, acceptance conditions and deliverables. Each retains its parent BRD Feature ID.

| BRD Feature | SOW Example | Typical Decomposition |
| --- | --- | --- |
| IAM-01 | Login / authentication | Login screen; credential validation; account status; session creation; error handling; role routing; audit behavior |
| APT-03 | Appointment booking | Doctor selection; slot validation; booking; duplicate prevention; confirmation; status; notification |
| QUE-03 | Live queue | Token state; position calculation; live refresh; staff view; patient view; delay handling |
| PHA-04 | Medication dispensing | Prescription validation; stock check; batch selection; partial dispensing; transaction; completion |
| INV-06 | Reorder / procurement | Threshold; request; supplier; PO; receiving; batch capture; stock update |
| AI-01 | Waiting-time prediction | Input preparation; inference; confidence/context; display; fallback; logging; feedback |

Important A detailed SOW/SRS item is not a new BRD feature. Feature count and implementation-item count must remain separate.

# 15. Requirements Change Control

1. Client communicates a requested change.

2. Business Analyst records the request, rationale and affected feature IDs.

3. Solution Architect assesses architecture, security, data and integration impact.

4. Business Analyst assesses business, scope, workflow and acceptance impact.

5. Project Manager / project team assesses effort, schedule and dependency impact.

6. BRD, SOW, SRS and backlog references are updated consistently.

7. Changed requirements receive a revision or Change Request identifier.

8. Until formal BRD sign-off, this document remains a living client-review baseline.

9. After sign-off, new requirements are handled as controlled Change Requests unless the client formally reopens the baseline.

# 16. Acceptance and Sign-Off Criteria

The client has reviewed the 78 BRD-level business capabilities.

Ambiguous business rules, role ownership and critical workflows are resolved or recorded as open decisions.

Scope classifications, boundaries, assumptions and dependencies are accepted.

Traceability exists from BRD feature → SOW item → SRS requirement → backlog item → test coverage.

Security, AI-safety, data ownership and recovery expectations are acknowledged.

The client formally approves the BRD baseline.

| Approval Role | Name / Signature | Date |
| --- | --- | --- |
| Client |  |  |
| Business Analyst |  |  |
| Solution Architect |  |  |
| Project Manager |  |  |

# 17. Traceability Key

| Artifact | Example |
| --- | --- |
| BRD | APT-03 — Appointment booking |
| SOW | APT-03-S01, APT-03-S02, … — detailed scope/delivery items |
| SRS | APT-03-FR-01, APT-03-FR-02, … — functional requirements |
| Test | TC-APT-03-01, TC-APT-03-02, … — verification coverage |
| Change | CR-2026-XXX — controlled client change affecting the feature |

# 18. Client Review Checklist

☐ Primary business scope is correctly represented.

☐ All 78 business-level features are understandable and at the right abstraction level.

☐ Required user roles and responsibilities are correct.

☐ Appointment and queue workflows are correct.

☐ Pharmacy and inventory workflows are correct.

☐ Supporting clinical, diagnostic, billing and inpatient scope is acceptable.

☐ AI boundaries are acceptable.

☐ Security, privacy, audit and recovery expectations are acceptable.

☐ Out-of-scope items are clear.

☐ Assumptions and dependencies are understood.

☐ Changes requested during review have been captured through the change-control process.

Sign-off effect Once formally signed off, this BRD becomes the approved baseline. New requirements should be handled through controlled Change Requests unless the client explicitly reopens the baseline.

END OF BUSINESS REQUIREMENTS DOCUMENT

Version 4.0 • Client Review Baseline